Action Items, March 14 VHEC Steering Committee meeting:

Attendees:

- Johanna Miller

- Dan Costin

- Dan Jones

- Barry McPhee

Action Items

| Action Item | Person/Team Responsible | Dates/ Deadline | Status |
| --- | --- | --- | --- |
| Confirm VHEC tabling for the Sat 3/16 Global Warming conference at MHS. | Dan Jones | 3/14/13 | Complete |
| Speak to Gwen and the VISTAs regarding access to any existing CAN email-lists and phone lists. | Barry; Dan Jones | 3/15/13 | Open |
| Develop Outreach raps | Barry; Johanna | 3/21/13 | In progress |
| Begin planning for March (3/27?) phone-a-thon | VHEC Committee | 3/15-3/27/13 | Open |
| Begin VHEC team use of a co-working website (Barry to write up/send a link to the site, and instructions for registration and use of same). | Barry | 3/17/13 | In progress |
| Begin planning for two “Door-to-door” weekends  Saturday, April 6  Saturday, April 20 | VHEC Committee | 3/18/13 | Open |
| Investigate use of CAN resources | Barry | 3/19/13 | Open |
| Look into access to VNRC and VPIRG member lists | Johanna | 3/21/13 | Open |
| Arrange for use of VNRC Meeting Room for use for the Phone-a-thon | Johanna | 3/21/13 | Open |
| Begin Planning for Home Energy Visits | Dan Costin | 4/1/13 | Open |

#  #  #